## Slide 1
Large Synoptic Survey Telescope
News since the May update
Astronomy & Astrophysics Advisory Committee
November 2012
Fred Borcherding/Nigel Sharp/Kathy Turner
<number>
Notes: <number>

## Slide 2
8.4 meter primary mirror
(6.7 m effective aperture)
3.3 gigapixel digital camera
3.5 deg field of view
30 terabytes of data nightly
Complete coverage of the
visible sky twice per week
10-yr primary mission
On Cerro Pachon, Chile
Current estimate $665M in
as-spent, then-year dollars,
assuming an NSF MREFC
start in July 2014 (NSF $466M,
DOE $160M, other $39M)
NSF/DOE JOG meets regularly
#1 recommendation in 2010 Astronomy & Astrophysics decadal survey
Project Summary
<number>

## Slide 3
Project Summary
Probing dark matter & dark energy
  Order of magnitude improvement
Mapping the Milky Way
  Formation and structure
An Inventory of the Solar System
  Potentially hazardous asteroids
The Transient Optical Sky
  Opening the Time Domain
A ten year experiment to reach specific scientific goals, with well defined deliverables
Not just another telescope – LSST is a data driven instrument with a prime mission of transformative discovery throughout astrophysics
Design driven by science requirements
Four Primary Science Goals
<number>

## Slide 4
<number>
Project Reviews
NSF Preliminary Design Review (PDR) – included camera &
interfaces from technical/managerial perspectives
“The Panel considers that the LSST project has
met the requirements for PDR.”
DOE CD-1 ‘Lehman’ review of the Camera
The project met all the CD-1 prerequisites “and in some areas has even significantly exceeded them” (DOE sign-off, April 2012)
Recommendations echoed by NSF’s internal MREFC process
  Anticipate that LSST should be the next project to receive NSF MREFC funds for construction, conditional on completion of:
  An NSF-DOE joint systems engineering review of the whole project
  6/01/2012: “LSST team has met the expected standards for this review.”
  A signed agreement with DOE in anticipation of a detailed Memorandum of Understanding (MOU)
  MOU signed 7/12/2012 (statement of intent signed 4/16/2012)

## Slide 5
<number>
Recommendations & Responses
NSF and DOE need to align their annual funding profiles
  Carried out shortly after CD-1 review.
  NSF scope was subject to a cost estimation review (CER), passed on May 16, 2012.
  CER recommended small changes that altered the TPC.
  NSF total project cost (TPC) $466M over 7 yrs, 3 mo
    Extended duration to synchronize with DOE camera funding
    Risk of increased TPC if annual funding profile cannot be met
  DOE total $160M
    Now properly synchronized with NSF request
Some other recommendations met or being met
Better quality assurance; total project systems engineering
  Two systems engineers hired (one senior, one junior)

## Slide 6
<number>
National Science Board
Major Actions & Approvals at the July 17-18, 2012 Meeting
Major actions and approvals at the 427th meeting of the Board included the following (not in priority order):
1. The Board authorized the Director, at his discretion, to include the construction of the Large Synoptic Survey Telescope (LSST) in a future budget. (NSB-12-31)
Result
When? Stay tuned – we don’t know

## Slide 7
<number>
Potential placement in NSF MREFC current plan
From the NSF FY13 budget request, with LSST added for illustration purposes

## Slide 8
<number>
Project coordinated timeline (if MREFC in FY14); camera delivery to summit July 2019

## Slide 9
<number>
M1/M3 Mirror Figuring
Final Optical Polishing has commenced – the last and most challenging step.
Final acceptance testing scheduled for late 2013.
5 tons of excess material already removed to generate rough optical surface of M1/M3.
Loose abrasive grinding resulted in initial optical shapes.
Interferogram shows surface deviations on the order of microns, aiming for nanometers.
Work enabled by private funds.
Recent Project Accomplishments

## Slide 10
<number>
Secondary mirror optical fabrication – bids reviewed, vendor selected, approval in hand
Substrate completed 11/09; in storage
Baseline scope - polishing
Optional scope - cell assembly system
Plant propagation continues at leveled telescope site in Chile
All environmental permits approved.
Vibrant desert ecosystem.
Program of rescue, relocation, and propagation to save endangered species has continued.
First specimen of Sandillón (Eriocyce aurata), propagated in a Univ. of La Serena laboratory, has been relocated to the greenhouse on Cerro Pachón.
Note that excavation provided level platforms and verified structural rock conditions.
Recent Project Accomplishments

## Slide 11
Recent Project Accomplishments
Fully functional prototype sensors received
Prototype meets major requirements (noise, format, sensitivity, flatness).
Sensor yield demonstration bids received - order underway.
Project on track to place sensor 1st article contract at the end of 2013.
Novel refrigerator developed and tested
Large focal plane (3,277 Megapixels) requires unprecedented cooling.
High capacity mixed-refrigerant system is new for astronomical cameras.
Now testing long transport lines
<number>

## Slide 12: LSSTCam
    DOE camera Project;
      June 2011 - Mission Need Statement signed for a “Stage IV” experiment; Critical Decision 0 (CD-0) approved; costs now accrue towards MIE total project cost
      Nov. 2011 - successful “Lehman” review of the camera project; in preparation for requesting CD-1 approval
      April 4, 2012 – CD-1 approval
      Q3FY14 – (planned @ CD-1) Approve Long Lead Procurements [ CD-3a ] – commence spending equipment money
      Q4FY15 – (planned @ CD-1) Approve Performance Baseline [ CD-2 ]
      Q4FY16 – (planned @ CD-1) Approve Start of Construction [ CD-3b ]
      Q1FY21 – (planned @ CD-1) Approve Project Completion [ CD-4 ]
    SLAC – lead lab in Camera Project
    BNL – major contributor for sensors and testing
    Other – other labs and universities contribute
<number>
<number>

## Slide 13: Joint Project – HEP view
    HEP is coordinating project planning
    with NSF
      Holding regular meetings of the Joint Oversight
      Group (JOG)
      Holding regular meetings with NSF and LSSTC
      Project Team
      HEP reviews will be attended by NSF; at least one
      DOE review per year and
      NSF reviews will be attended by HEP
    HEP project schedule based on Q4
    FY2014 NSF MREFC project start
<number>
<number>
  LSST – Large Synoptic Survey Telescope

## Slide 14
<number>
Recent NSF-DOE Success
Dark Energy Camera First Light 9/12/12
Dark Energy Survey (DES) due to begin this season, will run for five years

## Slide 15
LSST data policy
  LSST data policies are still in development.
  Data levels:
        Level 1 – nightly delivery of raw images and partial catalogs
        Level 2 – stacked images and combined catalogs
        Level 3 – external user-derived material
  Initial position:
    Transients – free, open, immediate access
    Levels 1 and 2 available to US and Chilean institutions when produced
    Level 2 data may be available worldwide with an annual release
    Level 3 data depends on the group producing it – these are outside LSST
  Data access leveraged against financial contributions to annual operations cost, quid-pro-quo access to other facilities (e.g. Euclid), or other contributions to the experiment, under terms yet to be negotiated.
  External groups will have access levels, probably not with unrestricted rights. They will also not have redistribution rights to use LSST data for any purpose or project they like.
  NSF-AST and DOE-HEP reserve approval rights over all agreements.
<number>

## Slide 16
<number>
LSST Operations Costs
Current estimate of $37M (FY11 $) annual operating costs
  MOU commits NSF and DOE to respective levels recommended by decadal survey, ~$19M and ~$9M
Remaining $9M to be covered by international partners
  $10.7M nominal in 69 letters of intent from 23 countries ($8.2M signed by Institute Directors or other management)
  32 participants from 29 potential international affiliates attended LSST All Hands Meeting, from 9 countries: Brazil, China, Hungary, Korea, New Zealand, Russia, Serbia, Switzerland, and the UK
  Expect to convert to firm commitments, in exchange for preferred project access, possibly including data access within proprietary period, after MREFC construction approval
Shortfalls are unlikely, but could be covered either by scope reductions (identified in PDR), or NSF/DOE decisions to increase contributions (discussed in MOU)
<number>
05/02/2012

## Slide 17
<number>
"If you can look into the seeds of time, and say which grain will grow and which will not, speak then unto me"
William Shakespeare
(Macbeth)

## Slide 18
<number>
Additional Information

## Slide 19
<number>
NSF-DOE Memorandum of Understanding
Entered clearance at both agencies 6/8/2012
  Common project baseline definition of scope, budget, schedule, and risk
  Agency oversight roles and responsibilities
  Integrated project office
  Development of mutually agreed data policy
  Operations contributions
  Exit and termination criteria
MOU was signed by DOE (Director of Office of Science) and NSF (Deputy Director) on July 12.

## Slide 20
<number>
Key deliverable Data Products and their production cadence

## Slide 21
<number>
angled shaft wall - effective
top “flap” - not effective
wall panel deflectors - effective
rounded edges - effective
Building Design Tests
Angled shaft wall, wind-channeling deflectors and curved edges proven effective and added to design
Original baseline
With wall panel deflectors
Wind direction
CFD model
with all
improvements
Example of 2010 CFD modeling Results

## Slide 22
<number>
pODI Full Field
(Sep. 13, 2012)
CCD-4
Blended Pair
Template
Model Fit
De-blended
Early results show excellent agreement with proven software
LSST wavefront sensing pipeline tested on new partial One Degree Imager (pODI) at WIYN
  LSST wavefront software is open source and is designed for general analysis of intra/extra focal image pairs.
Early commissioning tests show excellent agreement with obsolete, unsupported (but proven) software.
De-blending algorithm shown to be effective, maximizing the available sources.
LSST & ODI teams working together to analyze pODI alignment.
Recent Project Accomplishments

## Slide 23
<number>
LSST scalable database leverages worldwide community developments
Very successful XLDB-2012
300+ attendees
Strengthened team’s world-wide leadership position in extreme scale data management and analysis
Team instrumental in defining ArrayQL (a query language standard and algebra for array databases)
  Announced at XLDB-2012
Seriously exploring XLDB Consortium idea
  Announced at XLDB-2012
  Opportunity to attract serious funding
  ~20 companies responded so far
qserv packaged for easy multi-node install/admin and successfully installed by IN2P3
Demonstrated on Winter 2012 at AHM
Fine tuning qserv architecture: integrating with as alternative to
  Valuable proof that the database architecture is RDBMS agnostic
  Possible performance gains (columnar vs row-based technology)
  Working closely with the MonetDB team for qserv+MonetDB prototype later this year
150 node test accomplished last year
Large scale test on JHU hardware
  Planned scale: comparable to DR1 (1/4 PB)
  Exploring option of using ImSim to generate test data
qserv

## Slide 24
<number>
Broad uses for LSST data storage techniques recognized
Spherical partitioning with overlapping edges developed by LSST database team for efficient searching of enormous databases.
Technique shown to be linearly scalable without degrading system performance.
Useful in many fields that store spatial information (maps) and information that changes with time.
  Financial sector
  Geosciences; Climate modeling
  Fraud detection; internet usage behavior
  Medical imaging; Drug discovery
  Oil and gas exploration
Featured as a Research.gov highlight.

## Slide 25
<number>
2012 LSST All Hands Meeting
August 13 - 17, 2012
267 participants
  70 members of Science Collaborations
  102 Technical Team members
  32 participants from 29 potential International Affiliates
    5 days for formal in informal interactions
  22 plenary talks
  59 detailed working group breakouts
    144 participant survey responses
  85% extremely or quite productive
  93% extremely or quite likely to attend next AHM